[LIB NAME]

Unified LLM Client Library

Implementation Task & Subtask Report

Version 1.0  ·  April 2026  ·  CONFIDENTIAL

| Field | Detail |
| --- | --- |
| Library | [LIB NAME] — Unified LLM Client Library |
| Document | Implementation Task & Subtask Report v1.0 |
| Date | April 2026 |
| Providers | Anthropic (Claude), OpenAI (GPT/o-series), Google Gemini |
| Total Tasks | 23 tasks, 120+ subtasks |
| Total Phases | 7 phases |
| Estimated Total Effort | ~35–40 engineering days |
| Priority Levels | P0 = MVP blocker · P1 = Phase 2 required · P2 = Phase 3+ |

Inspiration: OpenAI Responses API OpenAI's Responses API (POST /responses) stores conversation state server-side and lets callers pass previous_response_id instead of the full history. Section T-19/T-20 implements the equivalent for our library — but provider-agnostic, stored in our own Postgres/Redis session store, supporting Anthropic + OpenAI + Gemini equally.

# Table of Contents

Summary & Effort Overview

# Summary & Effort Overview

All 23 tasks are broken into 7 phases. Each phase can be worked on in parallel within the phase where tasks are independent. Critical path: T-01 → T-02 → T-03 → T-08/T-09/T-10 → T-14/T-15 → T-18 → T-19.

| Phase | Scope | Tasks | Est. Effort | Key Deliverable |
| --- | --- | --- | --- | --- |
| Phase 1 | Foundation: project setup, types, utilities | T-01 → T-07 | 5–6 days | TypeScript skeleton with all shared utilities tested |
| Phase 2 | Provider adapters: raw fetch for all 3 providers | T-08 → T-10 | 7–8 days | All 3 providers working end-to-end with mock tests |
| Phase 3 | Conversation manager + session store | T-11 → T-13 | 5–6 days | Stateful conversations with context trimming + DB persistence |
| Phase 4 | Tool system + streaming + model router | T-14 → T-16 | 6–7 days | Complete tool calling across all providers. Unified streaming. |
| Phase 5 | LLMClient public API + cost/usage logging | T-17 → T-18 | 3–4 days | Ship-ready public API. Billing-grade cost tracking. |
| Phase 6 | Session API (Responses API equivalent) | T-19 → T-20 | 4–5 days | HTTP endpoints for stateful conversation management |
| Phase 7 | Testing, docs, perf benchmarks | T-21 → T-23 | 5–6 days | Full test coverage, docs, < 5ms overhead verified |

| Priority | Meaning | Count |
| --- | --- | --- |
| P0 | Must-have for MVP — do not ship without it | ~80% of tasks |
| P1 | Required for Phase 2 (post-MVP launch) | ~15% of tasks |
| P2 | Nice-to-have / future iteration | ~5% of tasks |

OpenAI Responses API — Key Learnings

# OpenAI Responses API — What We Learned & How We Adapt It

Fetched live from developers.openai.com/api/reference/resources/responses. The Responses API is OpenAI's replacement for the Assistants API — it manages conversation state server-side. Here is what it does and how we design our equivalent.

## 1. Endpoints

| Endpoint | Method | Purpose |
| --- | --- | --- |
| POST /responses | Create | Create a response. Optionally chain to previous via previous_response_id. |
| GET /responses/{id} | Read | Retrieve a stored response by ID. |
| DELETE /responses/{id} | Delete | Delete a stored response. |
| POST /responses/{id}/cancel | Cancel | Cancel an in-progress background response. |
| POST /responses/compact | Compact | Manually trigger context compaction on a response chain. |

## 2. The Key Mechanism: previous_response_id

Instead of passing the full conversation history on every call, you pass the ID of the previous response. OpenAI loads the conversation state from their servers. This means:

- Zero conversation history management in client code — just track one ID

- Context compaction is automatic: OpenAI manages token limits server-side

- Built-in conversation continuity without serialising/deserialising message arrays

- New system instructions can replace old ones without history carrying over

Our Equivalent Our POST /sessions/{id}/message serves the same purpose. You pass a sessionId instead of rebuilding message history. We load conversation state from our Postgres/Redis session store. The sessionId is our previous_response_id.

## 3. Context Management

| OpenAI Responses API | Our Library Equivalent |
| --- | --- |
| context_management parameter | Conversation contextStrategy option (sliding-window ¦ summarise) |
| compact_threshold: 1000 tokens | maxContextTokens threshold (90% of model limit by default) |
| POST /responses/compact endpoint | POST /sessions/{id}/compact — manual compaction trigger |
| Auto-compaction in-stream | Auto-trimming runs before every API call when threshold exceeded |
| CompactedResponse object | Our SummarisedConversation snapshot with summary message |

## 4. Streaming Events

OpenAI Responses API uses named SSE events unlike Chat Completions which uses unnamed data: chunks. Our canonical StreamChunk types are inspired by this cleaner naming:

| OpenAI Event | Our Canonical StreamChunk type |
| --- | --- |
| response.created | session.created (Session API only) |
| response.output_item.added | — (internal, not exposed) |
| response.output_text.delta | text-delta { delta: string } |
| response.output_text.done | — (inferred from done chunk) |
| response.completed | done { usage, finishReason } |
| response.failed | error { error: LLMError } |

## 5. Conversation Object

The Responses API has a conversation parameter that groups responses into a named conversation. Input/output items auto-appended. We implement the equivalent via our sessionId — every session IS a conversation. The session store auto-appends input and output on every send().

Phase 1 — Foundation

# Phase 1 — Foundation

Core project infrastructure. All utilities needed by every other component. Build this first — nothing else can start without it.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-01 | Project Setup | Initialise TypeScript monorepo, tsconfig, build pipeline, test framework, CI | P0 | 1 | 0.5d | — |
| T-01.1 | ↳ Init package.json | Name, version, exports map for treeshaking, engines: node>=18 | P0 | 1 | 1h | — |
| T-01.2 | ↳ tsconfig.json | strict:true, target:ES2022, moduleResolution:bundler, declaration:true, composite for project refs | P0 | 1 | 1h | — |
| T-01.3 | ↳ Build pipeline | tsup for dual CJS+ESM output. Single bundle per provider adapter for treeshaking. Source maps. | P0 | 1 | 2h | — |
| T-01.4 | ↳ Test framework | Vitest. Global test setup with mock fetch. Coverage reporter (>=90% target). E2E test tags. | P0 | 1 | 1h | — |
| T-01.5 | ↳ CI/CD | GitHub Actions: typecheck → lint → test → build on every PR. Fail on coverage drop. | P0 | 1 | 1h | — |
| T-01.6 | ↳ Linting | ESLint + Prettier. No-any rule on src/**. Import sort order enforced. | P0 | 1 | 1h | — |
| T-02 | Core Type Definitions | All shared TypeScript interfaces — the contract every adapter must satisfy | P0 | 1 | 1d | T-01 |
| T-02.1 | ↳ CanonicalMessage types | CanonicalRole, CanonicalMessage, CanonicalPart (text ¦ image ¦ tool_call ¦ tool_result) | P0 | 1 | 2h | — |
| T-02.2 | ↳ CanonicalResponse type | text, toolCalls, finishReason (union), model, provider, usage{inputTokens, outputTokens, cachedTokens, costUSD, cost}, raw | P0 | 1 | 2h | — |
| T-02.3 | ↳ StreamChunk types | Discriminated union: text-delta ¦ tool-call-start ¦ tool-call-delta ¦ tool-call-result ¦ done ¦ error | P0 | 1 | 2h | — |
| T-02.4 | ↳ CanonicalTool type | Tool definition schema — name, description, parameters (JSON Schema subset), execute() optional | P0 | 1 | 1h | — |
| T-02.5 | ↳ UsageEvent type | timestamp, provider, model, inputTokens, outputTokens, cachedTokens, costUSD, tenantId?, sessionId?, botId?, durationMs, finishReason | P0 | 1 | 1h | — |
| T-02.6 | ↳ Error class hierarchy | LLMError base → AuthenticationError, RateLimitError, ContextLimitError, ProviderCapabilityError, BudgetExceededError, MaxToolRoundsError, ProviderError | P0 | 1 | 2h | — |
| T-02.7 | ↳ Provider capability matrix type | ModelInfo: contextWindow, supportsVision, supportsTools, supportsStreaming, inputPrice, outputPrice, cacheReadPrice, cacheWritePrice | P0 | 1 | 1h | — |
| T-03 | Model Registry | Central database of all supported models with capabilities and pricing | P0 | 1 | 0.5d | T-02 |
| T-03.1 | ↳ prices.json | Adapt from LiteLLM MIT-licensed source. All 12 launch models. Fields: input/output/cacheRead/cacheWrite per 1M tokens. lastUpdated field. | P0 | 1 | 2h | — |
| T-03.2 | ↳ ModelRegistry class | list(), get(modelId), register(custom), isSupported(). Throws ProviderCapabilityError for unknown models. | P0 | 1 | 2h | — |
| T-03.3 | ↳ Capability check logic | Pre-call validation: tool calling, vision, streaming. Clear error message naming the unsupported feature + model. | P0 | 1 | 1h | — |
| T-03.4 | ↳ Price override API | LLMClient.updatePrices(overrides) merges into registry at runtime without library upgrade. | P0 | 1 | 1h | — |
| T-03.5 | ↳ Staleness warning | Dev-mode console warning if any model price.lastUpdated > 90 days. | P0 | 1 | 0.5h | — |
| T-04 | SSE Parser Utility | Zero-dependency SSE parser using native Node 18+ ReadableStream. Shared by all three provider adapters. | P0 | 1 | 0.5d | T-01 |
| T-04.1 | ↳ parseSSE() generator | AsyncGenerator<string>. Reads ReadableStream, TextDecoder, buffers partial lines, yields data: payloads. Skips [DONE]. | P0 | 1 | 2h | — |
| T-04.2 | ↳ Edge cases | Handle multi-line data: payloads, empty lines, comment lines (:), connection close mid-stream without sentinel. | P0 | 1 | 2h | — |
| T-04.3 | ↳ Unit tests | Test: normal stream, [DONE] sentinel, mid-stream close, chunked buffers, empty events, unicode safety. | P0 | 1 | 2h | — |
| T-05 | Retry & Backoff Utility | Shared retry logic with exponential backoff + jitter. Handles all three providers' rate limit patterns. | P0 | 1 | 0.5d | T-02 |
| T-05.1 | ↳ withRetry() function | maxAttempts (default 3), baseMs (1000), maxMs (30000). Returns Response or throws. Never retries 400/401/403. | P0 | 1 | 2h | — |
| T-05.2 | ↳ Retry-After header parsing | Parse numeric seconds, ISO date strings. Used by Anthropic + OpenAI. Falls back to exponential. | P0 | 1 | 1h | — |
| T-05.3 | ↳ Gemini retryDelay parsing | Parse retryDelay from error.details[]. Gemini does not use Retry-After headers. | P0 | 1 | 1h | — |
| T-05.4 | ↳ Jitter | Random jitter 0–500ms added to every backoff to prevent thundering herd. | P0 | 1 | 0.5h | — |
| T-05.5 | ↳ Unit tests | Test: 429 with Retry-After, 429 without header, 500 retry, 400 no-retry, max attempts exceeded. | P0 | 1 | 2h | — |
| T-06 | Cost Calculator | Per-call USD cost from token counts and prices.json. Accurate for cached tokens. | P0 | 1 | 0.5d | T-03 |
| T-06.1 | ↳ calcCostUSD() function | inputTokens, outputTokens, cachedReadTokens, cachedWriteTokens, model → USD number. Uses ModelRegistry prices. | P0 | 1 | 2h | — |
| T-06.2 | ↳ Cost formatter | formatCost(usd) → '$0.0023'. Handles sub-cent and large values gracefully. | P0 | 1 | 0.5h | — |
| T-06.3 | ↳ Provider usage normalisation | Three functions: anthropicUsageToCanonical(), openaiUsageToCanonical(), geminiUsageToCanonical(). Maps provider usage fields to {inputTokens, outputTokens, cachedTokens}. | P0 | 1 | 2h | — |
| T-06.4 | ↳ Unit tests | Test: all 12 models, cached tokens, zero-cost edge cases, unknown model returns 0. | P0 | 1 | 1h | — |
| T-07 | Token Estimator | Character-based token estimation for pre-flight context checks. No dependencies. | P0 | 1 | 0.25d | T-01 |
| T-07.1 | ↳ estimateTokens(text) | ~3.5 chars per token. Returns ceiling integer. For English; documented as ±10% accuracy. | P0 | 1 | 0.5h | — |
| T-07.2 | ↳ estimateMessageTokens(messages[]) | Sums content of all messages + ~4 tokens overhead per message. | P0 | 1 | 1h | — |
| T-07.3 | ↳ Provider counting API wrappers | anthropicCountTokens(), geminiCountTokens() — call provider's exact counting endpoint. Returns Promise<number>. Used when higher accuracy needed. | P0 | 1 | 3h | — |

Phase 2 — Provider Adapters

# Phase 2 — Provider Adapters

The three raw-fetch adapters. No SDK dependencies. Each adapter: translates canonical format → provider format, calls the API, translates response → canonical format, handles streaming, and maps errors to typed error classes.

⚠️ Gemini Gotchas for Implementers 1. Streaming uses a DIFFERENT endpoint (streamGenerateContent) — not stream:true on the same URL. 2. Role is 'model' not 'assistant'. 3. Tool args are already parsed objects — no JSON.parse needed. 4. finishReason STOP is ambiguous — check parts for functionCall to detect tool calls. 5. Rate limit retry delay is in error.details[].retryDelay, not a Retry-After header.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-08 | Anthropic Adapter | Raw fetch adapter for Anthropic Messages API. No SDK dependency. | P0 | 2 | 2d | T-02,T-04,T-05,T-06 |
| T-08.1 | ↳ Request translator | canonical messages[] → Anthropic format. Handle: system field extraction, role mapping, image blocks, tool_use/tool_result blocks, cache_control pass-through. | P0 | 2 | 3h | — |
| T-08.2 | ↳ Tool definition translator | CanonicalTool[] → Anthropic tools[] with input_schema. ToolChoice mapping. | P0 | 2 | 1h | — |
| T-08.3 | ↳ Response translator | Anthropic response → CanonicalResponse. Parse content blocks, stop_reason → finishReason, usage normalisation. | P0 | 2 | 2h | — |
| T-08.4 | ↳ fetch() call with auth | POST /v1/messages. Headers: x-api-key, anthropic-version: 2023-06-01, content-type. Wrap with withRetry(). | P0 | 2 | 1h | — |
| T-08.5 | ↳ SSE stream handler | Parse message_start, content_block_start, content_block_delta (text_delta + input_json_delta), content_block_stop, message_delta, message_stop. Buffer and JSON.parse tool input. | P0 | 2 | 4h | — |
| T-08.6 | ↳ Streaming tool reassembly | Accumulate input_json_delta fragments per content block index. JSON.parse on content_block_stop. Emit canonical tool-call-start/delta/result events. | P0 | 2 | 3h | — |
| T-08.7 | ↳ Error mapping | HTTP status + error.type → typed LLMError subclass. | P0 | 2 | 1h | — |
| T-08.8 | ↳ Integration tests | Mock fetch for all scenarios: text, tool call, streaming, cache hit, 429, 529. | P0 | 2 | 3h | — |
| T-09 | OpenAI Adapter | Raw fetch adapter for OpenAI Chat Completions API. No SDK dependency. | P0 | 2 | 2d | T-02,T-04,T-05,T-06 |
| T-09.1 | ↳ Request translator | Canonical → OpenAI format. Handle: developer role (not system), tool messages (role:'tool'), tool_call content null, image_url parts. | P0 | 2 | 3h | — |
| T-09.2 | ↳ Tool definition translator | CanonicalTool[] → [{type:'function', function:{name,description,parameters}}]. ToolChoice mapping. | P0 | 2 | 1h | — |
| T-09.3 | ↳ Response translator | OpenAI response → CanonicalResponse. JSON.parse(tool_calls[].function.arguments). usage normalisation including prompt_tokens_details.cached_tokens. | P0 | 2 | 2h | — |
| T-09.4 | ↳ fetch() call with auth | POST /v1/chat/completions. Header: Authorization: Bearer. stream_options:{include_usage:true} when streaming. Wrap withRetry(). | P0 | 2 | 1h | — |
| T-09.5 | ↳ SSE stream handler | Parse chat.completion.chunk deltas. Handle role in first chunk only. Accumulate partial tool arguments by tool_calls[].index. [DONE] sentinel. | P0 | 2 | 3h | — |
| T-09.6 | ↳ Streaming tool reassembly | Accumulate function.arguments across chunks per index. JSON.parse when finish_reason:'tool_calls'. Emit canonical stream events. | P0 | 2 | 3h | — |
| T-09.7 | ↳ Error mapping | HTTP status + error.code → typed LLMError subclass. | P0 | 2 | 1h | — |
| T-09.8 | ↳ Integration tests | Mock fetch: text, tools (parallel), streaming, cached tokens, reasoning model (o3), 429, 500. | P0 | 2 | 3h | — |
| T-10 | Gemini Adapter | Raw fetch adapter for Google Gemini generateContent + streamGenerateContent APIs. | P0 | 2 | 2.5d | T-02,T-04,T-05,T-06 |
| T-10.1 | ↳ Request translator | Canonical → Gemini format. system → systemInstruction.parts[{text}]. assistant → model role. Tool_call → functionCall part. Tool_result → functionResponse part in USER turn. | P0 | 2 | 4h | — |
| T-10.2 | ↳ Tool definition translator | CanonicalTool[] → {functionDeclarations:[...]}. UPPERCASE type names (STRING not string). ToolConfig from ToolChoice. | P0 | 2 | 2h | — |
| T-10.3 | ↳ Response translator | Gemini response → CanonicalResponse. candidates[0].content.parts. functionCall.args is already object (no parse). Detect tool call from parts (finishReason STOP is ambiguous). usageMetadata normalisation. | P0 | 2 | 3h | — |
| T-10.4 | ↳ generateContent fetch() | POST .../models/{model}:generateContent. Header: x-goog-api-key. Wrap withRetry() with Gemini-specific retryDelay parsing. | P0 | 2 | 2h | — |
| T-10.5 | ↳ streamGenerateContent fetch() | POST .../models/{model}:streamGenerateContent?alt=sse. DIFFERENT URL — not stream:true. Each SSE chunk is a full GenerateContentResponse, not a delta. | P0 | 2 | 2h | — |
| T-10.6 | ↳ Streaming text accumulation | Concatenate candidates[0].content.parts[0].text across chunks. Usage only accurate in final chunk (finishReason != null). | P0 | 2 | 2h | — |
| T-10.7 | ↳ Streaming function call handling | Function calls arrive as a complete functionCall object in one chunk — not streamed as fragments. Emit canonical tool-call-start + tool-call-result in one step. | P0 | 2 | 2h | — |
| T-10.8 | ↳ Error mapping | HTTP status + error.status (RESOURCE_EXHAUSTED etc.) → typed LLMError. Parse retryDelay from error.details. | P0 | 2 | 1h | — |
| T-10.9 | ↳ Integration tests | Mock fetch: text, tools, streaming (concatenation), function call in stream, SAFETY block, 429 with retryDelay. | P0 | 2 | 4h | — |

Phase 3 — Conversation Manager & Session Store

# Phase 3 — Conversation Manager & Session Store

The Conversation class is the core of the library's value proposition. It tracks state, manages context, and abstracts away the stateless nature of provider APIs. The Session Store makes this persistent — enabling the previous_response_id pattern.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-11 | Conversation Manager — Core | Stateful Conversation class. Central component. Tracks history, tokens, cost per session. | P0 | 3 | 2d | T-07,T-08,T-09,T-10 |
| T-11.1 | ↳ Conversation class skeleton | Constructor: sessionId, model, systemPrompt, contextStrategy, maxContextTokens, pinned[], budget. Internal state: messages[], tokenCount, totalCostUSD. | P0 | 3 | 2h | — |
| T-11.2 | ↳ conv.send(text ¦ parts) | Appends user message, calls provider via LLMClient, appends assistant response, updates tokenCount + totalCostUSD. Returns CanonicalResponse. | P0 | 3 | 3h | — |
| T-11.3 | ↳ conv.sendStream(text ¦ parts) | Same as send() but returns AsyncIterable<StreamChunk>. Updates state on 'done' chunk. | P0 | 3 | 2h | — |
| T-11.4 | ↳ Token count tracking | After every provider call, update from response.usage.inputTokens + outputTokens. Running total on conv.tokenCount. | P0 | 3 | 1h | — |
| T-11.5 | ↳ Cost accumulation | After every call, add response.usage.costUSD to conv.totalCostUSD. | P0 | 3 | 0.5h | — |
| T-11.6 | ↳ conv.serialise() / restore() | serialise() → plain JSON object (messages, tokenCount, totalCostUSD, model, sessionId, createdAt). Static restore(snapshot) → Conversation instance. | P0 | 3 | 2h | — |
| T-11.7 | ↳ conv.toMessages() | Returns current history as CanonicalMessage[]. For debugging/export. | P0 | 3 | 0.5h | — |
| T-11.8 | ↳ conv.clear() | Resets history (keeps system prompt). Resets tokenCount. Keeps totalCostUSD. | P0 | 3 | 0.5h | — |
| T-12 | Context Window Management | Automatic context trimming to prevent context limit errors. Pluggable strategies. | P0 | 3 | 1.5d | T-11 |
| T-12.1 | ↳ ContextManager interface | shouldTrim(messages[], tokenCount, limit): boolean. trim(messages[], tokenCount, limit): Promise<CanonicalMessage[]>. Pluggable via constructor. | P0 | 3 | 1h | — |
| T-12.2 | ↳ SlidingWindowStrategy | Remove oldest non-pinned messages until tokenCount < threshold (default 90% of model limit). O(n) pass. | P0 | 3 | 3h | — |
| T-12.3 | ↳ Pinned message support | messages marked pinned:true are never removed. System prompt always pinned by default. Last user message always pinned. | P0 | 3 | 2h | — |
| T-12.4 | ↳ Pre-call trim check | Before every API call, run context check. If tokenCount > threshold, apply strategy. Log trim event. | P0 | 3 | 1h | — |
| T-12.5 | ↳ SummarisationStrategy (Phase 4) | When near limit: call cheap model (Haiku/Flash) to summarise oldest N messages. Replace with summary message. Mark summary with metadata. | P1 | 3 | 4h | — |
| T-12.6 | ↳ Unit tests | Test: sliding window removes correct messages, pinned messages preserved, trim not triggered below threshold, multiple trim cycles. | P0 | 3 | 2h | — |
| T-13 | Session Store Interface | Pluggable persistence layer for conversation state. Inspired by OpenAI Responses API's server-side state. | P0 | 3 | 1d | T-11 |
| T-13.1 | ↳ SessionStore interface | get(sessionId): Promise<ConversationSnapshot ¦ null>. set(sessionId, snapshot): Promise<void>. delete(sessionId): Promise<void>. list(tenantId): Promise<SessionMeta[]>. | P0 | 3 | 1h | — |
| T-13.2 | ↳ InMemorySessionStore | Map<string, ConversationSnapshot>. Default store. Useful for testing and single-process deployments. | P0 | 3 | 1h | — |
| T-13.3 | ↳ PostgresSessionStore | Uses pg or postgres.js. Stores snapshot as JSONB. Tenant-scoped with RLS. Indexed on (tenant_id, session_id, updated_at). | P0 | 3 | 3h | — |
| T-13.4 | ↳ RedisSessionStore | Uses ioredis. Stores snapshot as JSON string. TTL-based expiry. Useful for high-throughput deployments. | P0 | 3 | 3h | — |
| T-13.5 | ↳ Session metadata | SessionMeta: sessionId, tenantId, messageCount, tokenCount, totalCostUSD, model, createdAt, updatedAt. | P0 | 3 | 1h | — |
| T-13.6 | ↳ Auto-save on send() | After every conv.send() call, if a SessionStore is configured, auto-call store.set(sessionId, conv.serialise()). | P0 | 3 | 1h | — |

Phase 4 — Tools, Streaming & Model Router

# Phase 4 — Tool System, Streaming & Model Router

The three subsystems that make the library production-grade: a unified tool calling abstraction that works across all providers, a consistent streaming interface with canonical chunk types, and a rule-based model router for cost/latency optimisation.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-14 | Unified Tool System | defineTool() API. Single tool definition works across all three providers. Auto-execute loop. | P0 | 4 | 2d | T-08,T-09,T-10 |
| T-14.1 | ↳ defineTool() function | Takes name, description, parameters (JSON Schema), execute() optional. Returns typed CanonicalTool. Full TypeScript inference for args type from parameters schema. | P0 | 4 | 3h | — |
| T-14.2 | ↳ Canonical → Anthropic translation | CanonicalTool → {name, description, input_schema}. ToolChoice mapping (auto/any/none/specific). | P0 | 4 | 1h | — |
| T-14.3 | ↳ Canonical → OpenAI translation | CanonicalTool → {type:'function', function:{name,description,parameters}}. tool_choice mapping. | P0 | 4 | 1h | — |
| T-14.4 | ↳ Canonical → Gemini translation | CanonicalTool[] → {functionDeclarations:[...]} with UPPERCASE types. toolConfig from ToolChoice. | P0 | 4 | 1.5h | — |
| T-14.5 | ↳ Tool result normalisation | canonical tool_result → Anthropic user+tool_result ¦ OpenAI role:tool ¦ Gemini user+functionResponse. Handles all three formats. | P0 | 4 | 2h | — |
| T-14.6 | ↳ Auto-execute loop | When executeTools:true: detect tool calls, run execute() (with timeout 30s), format results, append to messages, call API again. Loop until stop or maxToolRounds. | P0 | 4 | 4h | — |
| T-14.7 | ↳ Parallel tool execution | When model returns multiple tool calls simultaneously, run all execute() calls via Promise.all(), not sequentially. | P0 | 4 | 2h | — |
| T-14.8 | ↳ MaxToolRounds guard | After N rounds (default 5), throw MaxToolRoundsError with last response. Prevents infinite agentic loops. | P0 | 4 | 1h | — |
| T-14.9 | ↳ Tool error handling | If execute() throws, catch error, return {success:false, error:message} as tool result. Model can react gracefully. | P0 | 4 | 1h | — |
| T-15 | Streaming System | Unified AsyncIterable<StreamChunk> interface across all providers. Consistent event types. | P0 | 4 | 1.5d | T-08,T-09,T-10 |
| T-15.1 | ↳ StreamChunk discriminated union | text-delta{delta}, tool-call-start{id,name}, tool-call-delta{id,argsDelta}, tool-call-result{id,name,result}, done{usage,finishReason}, error{error}. | P0 | 4 | 1h | — |
| T-15.2 | ↳ Anthropic stream assembler | Stateful class: converts Anthropic SSE events → canonical StreamChunks. Buffers input_json_delta, emits tool-call-start on content_block_start, done on message_stop. | P0 | 4 | 3h | — |
| T-15.3 | ↳ OpenAI stream assembler | Stateful class: converts OpenAI chunks → canonical StreamChunks. Accumulates arguments by tool_calls[].index, emits tool events when finish_reason:tool_calls. | P0 | 4 | 3h | — |
| T-15.4 | ↳ Gemini stream assembler | Stateful class: converts Gemini chunks (complete response objects) → canonical StreamChunks. Concatenate text. Function calls arrive complete in one chunk. | P0 | 4 | 3h | — |
| T-15.5 | ↳ AbortController support | llm.stream() accepts an AbortSignal. Passed to fetch() options. Cancels the underlying HTTP request immediately. | P0 | 4 | 1h | — |
| T-15.6 | ↳ Stream + tools integration | When tools present and model makes a tool call mid-stream: pause stream, execute tool, inject result, resume with new API call. Emit tool-call-* events during. | P0 | 4 | 4h | — |
| T-16 | Model Router | Rule-based model selection. Fallback on provider failure. A/B testing. | P0 | 4 | 1d | T-08,T-09,T-10 |
| T-16.1 | ↳ ModelRouter class | Constructor takes rules[] and fallback. Each rule: when(context):boolean, use:string. Evaluated in order, first match wins. | P0 | 4 | 2h | — |
| T-16.2 | ↳ Routing context | RouterContext: messages[], tenantId?, botId?, botConfig?, sessionTokenCount, estimatedInputTokens. | P0 | 4 | 1h | — |
| T-16.3 | ↳ Fallback on provider error | If primary model throws ProviderError or RateLimitError after maxAttempts, automatically retry with fallback model. | P0 | 4 | 2h | — |
| T-16.4 | ↳ A/B weight routing | Rule can have weight:0.8 — route 80% of matching traffic to primary, 20% to secondary. Uses seeded random for consistency. | P0 | 4 | 2h | — |
| T-16.5 | ↳ Router logging | Log which rule matched (or fallback used) in UsageEvent.routingDecision field. Useful for analytics. | P0 | 4 | 1h | — |

Phase 5 — LLMClient Public API & Cost Tracking

# Phase 5 — LLMClient Public API & Cost Tracking

The public interface that consumers actually import. Ties all components together. Also where the billing-grade cost tracking and the pluggable UsageLogger live.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-17 | Cost Tracking & Usage Logger | Per-call + per-session + per-tenant cost tracking. Pluggable logger interface. | P0 | 5 | 1.5d | T-06,T-11 |
| T-17.1 | ↳ UsageLogger interface | { log(event: UsageEvent): Promise<void> }. Errors in logger never propagate — caught and emitted as 'logger-error' event on client. | P0 | 5 | 1h | — |
| T-17.2 | ↳ ConsoleLogger | Default logger. Pretty-prints UsageEvent to console in development. Omits in production (NODE_ENV check). | P0 | 5 | 0.5h | — |
| T-17.3 | ↳ PostgresUsageLogger | Writes UsageEvent to usage_events table. Matches the parent platform schema. Batches writes (flush every 100ms or 10 events). | P0 | 5 | 3h | — |
| T-17.4 | ↳ Budget guard — per call | budget.maxCostUSD checked against estimated cost (inputTokens estimate × price) before API call. Throws BudgetExceededError if over. | P0 | 5 | 2h | — |
| T-17.5 | ↳ Budget guard — per session | budget.maxSessionCostUSD checked on conv.totalCostUSD after each turn. Throws BudgetExceededError. Configurable action: throw ¦ warn ¦ skip. | P0 | 5 | 2h | — |
| T-17.6 | ↳ client.getUsage() query API | getUsage({tenantId, from, to, groupBy}) returns aggregated UsageStats if PostgresUsageLogger configured. Groups by model, day, tenant. | P0 | 5 | 3h | — |
| T-18 | LLMClient — Public API Surface | Main entry point. Orchestrates all components. The public-facing class consumers import. | P0 | 5 | 1d | T-08,T-09,T-10,T-14,T-15,T-16,T-17 |
| T-18.1 | ↳ LLMClient constructor | Options: defaultModel, defaultProvider, tenantId, router, sessionStore, usageLogger, retryConfig, budget. Validates all options at init. | P0 | 5 | 2h | — |
| T-18.2 | ↳ llm.complete(options) | Non-streaming call. Resolves routing, builds request, calls adapter, runs tool loop if tools present, returns CanonicalResponse. | P0 | 5 | 2h | — |
| T-18.3 | ↳ llm.stream(options) | Streaming call. Returns AsyncIterable<StreamChunk>. Tools mid-stream handled. | P0 | 5 | 2h | — |
| T-18.4 | ↳ llm.conversation(options) | Returns a new Conversation instance. Wires up sessionStore, usageLogger, budget from client config. Auto-loads snapshot from store if sessionId + store configured. | P0 | 5 | 2h | — |
| T-18.5 | ↳ llm.models registry proxy | llm.models.list(), llm.models.get(), llm.models.register() — delegate to ModelRegistry. | P0 | 5 | 0.5h | — |
| T-18.6 | ↳ Mock provider for testing | LLMClient.mock({responses: [...]}) — returns a client whose adapter returns configured CanonicalResponses without HTTP calls. Configurable delays. | P0 | 5 | 2h | — |

Phase 6 — Session API (Responses API Equivalent)

# Phase 6 — Session API

HTTP endpoints that expose conversation state management as a service. This is our equivalent of OpenAI's Responses API — but provider-agnostic and backed by our own Postgres/Redis store. Any client can use sessionId instead of managing conversation history manually.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-19 | Session API — Conversation Endpoints | HTTP API layer inspired by OpenAI Responses API. Stateful session management over our DB. Allows previous_session_id pattern. | P0 | 6 | 2d | T-13,T-18 |
| T-19.1 | ↳ POST /sessions | Create a new session. Body: {model, systemPrompt, tenantId, botId, config}. Returns: {sessionId, createdAt, status:'idle'}. | P0 | 6 | 2h | — |
| T-19.2 | ↳ POST /sessions/{id}/message | Send a message to an existing session. Loads snapshot from store, appends message, calls LLM, saves updated snapshot. Body: {content, stream?}. Returns: CanonicalResponse or SSE stream. This is the previous_response_id equivalent. | P0 | 6 | 4h | — |
| T-19.3 | ↳ GET /sessions/{id} | Get session metadata + full message history. Returns: SessionMeta + messages[]. Supports ?include=messages,usage,cost. | P0 | 6 | 1h | — |
| T-19.4 | ↳ GET /sessions/{id}/messages | Paginated message history. Params: limit, before, after (cursor). Returns: {messages[], hasMore, nextCursor}. | P0 | 6 | 2h | — |
| T-19.5 | ↳ DELETE /sessions/{id} | Delete session and all messages from store. Returns 204. GDPR-compliant erasure. | P0 | 6 | 1h | — |
| T-19.6 | ↳ POST /sessions/{id}/compact | Manually trigger context compaction (summarisation strategy). Returns compacted session metadata. Mirrors OpenAI's /responses/compact endpoint. | P0 | 6 | 2h | — |
| T-19.7 | ↳ POST /sessions/{id}/fork | Fork a session at a given message index. Creates new session from that point. Useful for A/B testing different system prompts. | P0 | 6 | 2h | — |
| T-19.8 | ↳ GET /sessions | List sessions for a tenant. Supports filters: model, status, from/to date, limit/cursor. Returns: SessionMeta[]. | P0 | 6 | 2h | — |
| T-19.9 | ↳ Session streaming | POST /sessions/{id}/message with stream:true returns SSE. Events mirror canonical StreamChunks: session.text.delta, session.tool_call.start, session.done, session.error. | P0 | 6 | 3h | — |
| T-19.10 | ↳ Middleware: tenant auth | Every endpoint validates tenantId from JWT or API key header. Sets DB session context for RLS. | P0 | 6 | 2h | — |
| T-20 | Session API — OpenAI Responses API Mapping | Design notes for how our Session API maps to OpenAI Responses API concepts | P0 | 6 | 0.5d | T-19 |
| T-20.1 | ↳ previous_response_id equivalent | Our POST /sessions/{id}/message IS the equivalent. Pass sessionId instead of rebuilding message history. We load state from DB; OpenAI loads from their servers. | P0 | 6 | Design | — |
| T-20.2 | ↳ conversation parameter | Our sessionId maps to OpenAI's conversation parameter. Inputs auto-appended after each response. | P0 | 6 | Design | — |
| T-20.3 | ↳ context_management / compact_threshold | Our Conversation.maxContextTokens + contextStrategy maps to context_management.compact_threshold. Auto-triggered on threshold. | P0 | 6 | Design | — |
| T-20.4 | ↳ background parameter | Our POST /sessions/{id}/message can be async (jobId returned, webhook on completion). Phase 4 enhancement. | P1 | 6 | Future | — |
| T-20.5 | ↳ include parameter | Our GET ?include=messages,usage,cost maps to OpenAI's include[] for additional output data. | P0 | 6 | Design | — |

Phase 7 — Testing, Documentation & Performance

# Phase 7 — Testing, Documentation & Performance

Everything needed to ship with confidence: comprehensive test coverage, full API documentation, and verified performance benchmarks.

| ID | Task / Subtask | Description & Acceptance Criteria | Pri | Phase | Effort | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| T-21 | Testing — Integration & E2E | Full integration test suite across all providers using mocks + optional live API tests | P0 | 7 | 2d | T-18,T-19 |
| T-21.1 | ↳ Provider mock servers | Lightweight HTTP servers (using node:http) that return realistic provider-specific responses for: text, tool call, streaming, error scenarios. | P0 | 7 | 4h | — |
| T-21.2 | ↳ Cross-tenant isolation tests | Prove that ConversationA's history never bleeds into ConversationB. Automated assertion after every deployment. | P0 | 7 | 2h | — |
| T-21.3 | ↳ Tool call round-trip tests | For each provider: send tool-calling request → verify correct format sent → return mock tool result → verify final response. All 3 providers. | P0 | 7 | 3h | — |
| T-21.4 | ↳ Context trimming tests | Simulate long conversation, verify sliding window removes correct messages, verify pinned messages preserved. | P0 | 7 | 2h | — |
| T-21.5 | ↳ Cost accuracy tests | Compare calculated cost vs expected for all 12 models. Tolerance ±1%. | P0 | 7 | 1h | — |
| T-21.6 | ↳ Session API tests | Full lifecycle: create session → send messages → get history → fork → compact → delete. | P0 | 7 | 3h | — |
| T-21.7 | ↳ Live API smoke tests (optional) | Gated by env var LIVE_TESTS=1. Sends 1 real request to each provider. For pre-release validation only. Not in CI. | P0 | 7 | 2h | — |
| T-22 | Documentation | JSDoc, README, API reference, migration guide | P1 | 7 | 2d | T-18 |
| T-22.1 | ↳ JSDoc on all public APIs | Every exported function, class, method, and type. Include @example blocks for the most common patterns. | P1 | 7 | 4h | — |
| T-22.2 | ↳ README.md | Quick start (15 lines to first response), provider setup, feature overview, link to full docs. | P1 | 7 | 2h | — |
| T-22.3 | ↳ API reference (auto-generated) | typedoc generates HTML from JSDoc. Published to GitHub Pages on release. | P1 | 7 | 1h | — |
| T-22.4 | ↳ Provider comparison guide | Table: which features work on which providers. Format differences. When to use each. | P1 | 7 | 2h | — |
| T-22.5 | ↳ Migration guide (from raw SDKs) | Before/after examples for Anthropic SDK → [LIB], openai npm → [LIB], @google/generative-ai → [LIB]. | P1 | 7 | 3h | — |
| T-22.6 | ↳ CHANGELOG.md | Conventional commits. Every release entry: what changed, why, breaking change migration steps. | P1 | 7 | 1h | — |
| T-23 | Performance & Benchmarking | Verify < 5ms overhead target. Bundle size checks. | P1 | 7 | 1d | T-18 |
| T-23.1 | ↳ Latency benchmark | Measure time from llm.complete() call to provider fetch() call. Must be < 5ms for all paths. Use node:perf_hooks. | P1 | 7 | 2h | — |
| T-23.2 | ↳ Bundle size check | Build and check: full bundle < 150KB gzipped. Individual provider adapter < 15KB gzipped. Automated check in CI. | P1 | 7 | 1h | — |
| T-23.3 | ↳ Memory leak check | Run 10,000 conversation turns in a loop. Verify no memory growth. Use node --inspect and heap snapshots. | P1 | 7 | 2h | — |
| T-23.4 | ↳ Concurrent session test | 100 concurrent Conversation instances sending messages simultaneously. Verify no cross-contamination, no deadlocks. | P1 | 7 | 2h | — |

Critical Path & Dependencies

# Critical Path & Dependencies

The critical path is the minimum sequence of tasks that determines the earliest ship date. All items on the critical path must be done sequentially — they cannot be parallelised.

| Step | Task | Unblocks | Est. Days |
| --- | --- | --- | --- |
| 1 | T-01: Project Setup | Everything | 0.5d |
| 2 | T-02: Core Types | All adapters, all utilities | 1d |
| 3 | T-03: Model Registry | Cost calc, capability checks | 0.5d |
| 4 | T-04–T-07: Utilities (parallel) | SSE, retry, cost, tokens | 2d |
| 5 | T-08: Anthropic Adapter | T-11, T-14, T-18 | 2d |
| 6 | T-09+T-10: OpenAI+Gemini Adapters (parallel with T-08) | Same as above | 2d |
| 7 | T-11: Conversation Manager Core | T-12, T-13, T-19 | 2d |
| 8 | T-12: Context Window Mgmt | T-19 | 1.5d |
| 9 | T-13: Session Store | T-19 | 1d |
| 10 | T-14: Tool System | T-18 | 2d |
| 11 | T-15: Streaming System | T-18 | 1.5d |
| 12 | T-16: Model Router | T-18 | 1d |
| 13 | T-17: Cost Tracking | T-18 | 1.5d |
| 14 | T-18: LLMClient Public API | T-19, T-21, T-22 | 1d |
| 15 | T-19: Session API | T-20, T-21 | 2d |
| 16 | T-21–T-23: Test + Docs + Perf (parallel) | Ship | 5d |

Parallelisation Opportunities T-08, T-09, T-10 (provider adapters) can all be built simultaneously by different engineers — they share the same interface (T-02) but have no code dependencies on each other. Similarly T-04/T-05/T-06/T-07 (utilities) can be built in parallel. T-21/T-22/T-23 (testing, docs, perf) can run concurrently at the end.

[LIB NAME] Implementation Task Report  ·  v1.0  ·  April 2026  ·  CONFIDENTIAL